## Sheet1
PROJECT PHASES |  | TIME (HOURS) | TOTAL HOURS
Phase 1 | PROJECT SETUP AND PLANNING | 10
1.1 | Create GitHub Repository | 0.5 | X
1.2 | Set Up Kanban Board | 0.5 | X
1.3 | Define Project Structure (Backend, Frontend, Database) | 3 | X
1.4 | Finalize API + Data Model Design | 3
1.5 | Choose Hosting (Optional) | 3
Phase 2 | BACKEND DEVELOPMENT (DJANGO) | 40
PHASE 2.1 | DJANGO PROJECT SETUP | 8
2.1.1 | Install Django + Django REST Framework | 1
2.1.2 | Set Up Virtual Environment | 1
2.1.3 | Create Django Project + App Structure | 2
2.1.4 | Configure Database | 2
2.1.5 | Set Up Environment Variables (API Keys, DB Configs) | 2
PHASE 2.2 | USER AUTHENTICATION | 7
2.2.1 | Create User Model (Username, Password, Email ect.) | 2
2.2.2 | Implement User Registration + Login (JWT/Auth Tokens) | 3
2.2.3 | Set Up Password Hashing + Security Measures | 1
2.2.4 | Ass User Email Notifications (SMTP/Third-Party Service) | 1
PHASE 2.3 | MOVIE DATA HANDLING | 6
2.3.1 | Connect TMDb API + Fetch Movie Data | 2
2.3.2 | Store Retrieved Movies in the Database | 2
2.3.3 | Fetch Movie Cast + Store Actor Data | 2
PHASE 2.4 | USER REVIEWS + SENTIMENT ANALYSIS | 9
2.4.1 | Fetch Movie Reviews from TMDb API | 2
2.4.2 | Implement Sentiment Analysis (VADER/TextBlob) | 3
2.4.3 | Store Processed Reviews in the Database | 2
2.4.4 | Create API Endpoint to Retrieve Reviews + Sentiments | 2
PHASE 2.5 | WATCHLIST FEATURE | 5
2.5.1 | Implement Watchlist Model in Database | 1
2.5.2 | Create API Endpoints for Watchlist Operations (Add/Remove Movie) | 2
2.5.3 | Automate Weekly Watchlist Email Reports | 2
PHASE 2.6 | API TESTING + DEBUGGING | 9
2.6.1 | Write Unit Tests for Movie API Calls | 2
2.6.2 | Test User Authentication API | 2
2.6.3 | Validate Review Sentiment Analysis Accuracy | 3
2.6.4 | Optimize API Performance + Rate-Limit Handling | 2
PHASE 3 | FRONTEND DEVELOPMENT (REACT) | 38
PHASE 3.1 | REACT PROJECT SETUP | 5
3.1.1 | Set Up React App (Vite/Create-React-App) | 1
3.1.2 | Configure Routing (React Router) | 1
3.1.3 | Set Up State Management (Redux or Context API) | 3
PHASE 3.2 | USER INTERFACE (UI) | 14
3.2.1 | Create Landing Page with Search Bar | 3
3.2.2 | Build Movie Detail Page (Cast, Reviews, Sentiment Score) | 3
3.2.3 | Implement Movie Comparison Page | 3
3.2.4 | Develop Watchlist Management Page | 3
3.2.5 | Build User Profile ( Account Settings, Notifications, Watchlist) | 2
PHASE 3.3 | BACKEND INTEGRATION | 7
3.3.1 | Connect React App to Django API | 2
3.3.2 | Implement API Calls for Search + Movie Details | 2
3.3.3 | Implement User Authentication in React (JWT Login/Signup) | 2
3.3.4 | Display Sentiment Analysis Results on UI | 1
PHASE 4 | DEPLOYMENT + AUTOMATION | 20
PHASE 4.1 | BACKEND DEPLOYMENT | 8
4.1.1 | Set Up Django Backend on a Cloud Server (AWS, Render, DigitalOcean, etc.) | 3
4.1.2 | Configure SQL on the Server | 2
4.1.3 | Set Up API Rate-Limiting + Security Features | 3
PHASE 4.2 | FRONTEND DEPLOYMENT | 6
4.2.1 | Deploy React App on Vercel/Netlify | 2
4.2.2 | Connect Frontend with Backend API | 2
4.2.3 | Ensure HTTPS + Secure API Calls | 2
PHASE 4.3 | AUTOMATIONS + MONITORING | 6
4.3.1 | Set Up CI/CD Pipelines for Automatic Deployments | 2
4.3.2 | Automate Weekly Email Reports | 2
4.3.3 | Set Up Logging + Error Monitoring (Sentry, LongRocket, etc.) | 2
PHASE 5 | TESTING + FINAL LAUNCH | 14
5.1 | Conduct End-to-End Testing | 4
5.2 | Gather Beta User Feedback | 3
5.3 | Fix Reproted Issues + Optimize Performance | 4
5.4 | Prepare Documentation for Deployment + User Guide | 3
5.5 | Officially Launch the Application | 0